## Business case
VAVEhub · VE Toolkit
Business Case
Blue cells are yours to change; shaded cells work themselves out. Filled in with the bracket example from Module 7: replace the numbers with your own.
Idea: |  | Champion:
What it saves
Item | Value | Notes
Saving per unit (£) | 0.3 | Checked by finance, not by the idea's biggest supporter
Annual volume (units) | 300000
Annual saving |  | Saving per unit × volume
What it costs to bring in (one-time)
Item | Value | Notes
Tooling (£) | 38000
Validation and testing (£) | 7000 | Only climb the testing ladder as far as the risk needs
Engineering hours | 120
Engineering rate (£ an hour) | 65
Scrapped stock (£) | 0
Re-approval: PPAP, re-certification (£) | 0
Total one-time cost |  | Tooling + testing + engineering + scrap + re-approval
When it happens, and when it pays back
Item | Value | Notes
Months until the change is made | 4 | Savings start on the day the change is made, not the day it's approved
Remaining product life (years) | 4
Payback (months) |  | One-time cost ÷ annual saving × 12. Aim for under 12 months
Years of savings |  | Remaining life minus the time until the change is made
Net saving over the product's life |  | Annual saving × years of savings − one-time cost
What each month of delay costs
Verdict
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited

## Risks
VAVEhub · VE Toolkit
What could go wrong
Score the change from the current design. RPN = severity × occurrence × detection (1–10 each). Watch the change in RPN, not just the number.
New way it could fail | Severity | Occurrence now | Occurrence after | Detection | RPN now | RPN after | Action | Test step (1–5)
Example: cut edge in poor condition (fine-blanked bracket) | [6 empty] | Service the die at set intervals
Testing ladder: 1 desk calculation · 2 CAE or simulation · 3 rig test · 4 production-line trial · 5 field trial.
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited