## Charter
VAVEhub · VE Toolkit
VE Programme Charter
One page: why the programme exists, who runs it, how it's measured and when it meets.
Business / site: |  | Sponsor:
Purpose and scope
Item | Answer | Notes
Why we're running a programme |  | One sentence
Product lines in scope
Out of scope
Savings target this year (£)
Savings target (% of product cost) |  | A first round usually finds 8–15%; established programmes 3–5% a year
Engineering time funded (people or hours) |  | A target bigger than the time you've paid for becomes a number nobody owns
The value board
Role | Name | What they do
Sponsor (chairs the board) |  | Makes decisions, removes blockers
Programme lead / facilitator |  | Runs studies and the savings funnel
Finance |  | Checks every saving against the fixed starting cost
Engineering
Purchasing
Manufacturing and quality
The monthly review (30 minutes)
Minutes | Item | Who
0–5 | Savings confirmed at L4 since last month | Finance
5–15 | Ideas that haven't moved since the last review: owner, blocker, new date | Programme lead
15–25 | Decisions on business cases at L2 | Value board
25–30 | Actions, owners and dates | Programme lead
The year
When | What | Owner
Every month | Funnel review
Every quarter (months 3, 6, 9, 12) | Choose the next products to study and the next teardowns
Every year | Value plan for each product line, linked to its margin plan; an internal value day
Training | Who is trained, to what level, by when
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited

## KPIs
VAVEhub · VE Toolkit
KPIs: pick three to start
Set Track to Y for the ones you'll report. Status works itself out once you fill in Target and Now.
Track? | KPI | How it's measured | Target | Higher is better? | Owner | Now | Status
| Funnel coverage | % of product cost being actively studied | 60% | Y
| Cost visibility | % of the parts list with a should-cost | 80% | Y
| Ideas implemented | % of approved ideas that reach production |  | Y
| Savings arriving | £ of checked savings in production each quarter |  | Y
| Average payback | One-time cost ÷ annual saving, in months | 12 | N
| Idea reuse | Ideas reused on other product lines |  | Y
Y
Worked example, year 2 (Module 12): funnel coverage 64%, cost visibility 83%, 41% of approved ideas implemented, £1.9M of checked savings a quarter, average payback 8.2 months.
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited

## Monthly review log
VAVEhub · VE Toolkit
Monthly review log
One line per review. The running total counts only savings confirmed at L4.
Date | Who attended | L4 savings confirmed (£) | Running total (£) | Decisions | Actions (owner, date)
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited