## Stage Definitions
VAVEhub · VE Toolkit
Savings Funnel — Stage Definitions
The four gates every idea passes. Only L4 counts to the P&L.
Stage | Entry criteria
L1 · Idea | Logged with an owner and a rough saving — no validation yet.
L2 · Validated | Business case drafted: saving, one-time cost, risk and validation plan agreed.
L3 · Implemented | Change made in production / PPAP cleared.
L4 · Audited | Saving confirmed against the frozen baseline by finance — now it counts.
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited. Designed & Developed by Avinash Bhosale.

## Pipeline
VAVEhub · VE Toolkit
Savings Funnel — Pipeline
One idea per row. Payback calculates from saving & one-time cost. Add rows for your whole pipeline.
ID | Idea title | Stage | Gross saving €/yr | One-time cost € | Payback (mo) | Owner | Next gate date | Status note
ID-01 | Snap-fit housing | L2 Validated | 42000 | 45000 |  | J. Doe |  | CAE sign-off pending
ID-02 | Down-gauge wall | L3 Implemented | 28000 | 12000 |  | A. Rao |  | PPAP in progress
Total pipeline €/yr →
Stage is a dropdown (L1→L4). Payback (months) = one-time cost × 12 ÷ gross annual saving, calculated automatically. Totals sum the whole pipeline. Review monthly — every idea needs an owner, a stage and a next-gate date.
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited. Designed & Developed by Avinash Bhosale.